DRAFT

REDD+ SAFEGUARDS ACTION PLAN (SAP) FOR

PARTNERSHIP FOR PRODUCTIVITY, PROTECTION AND RESILIENCE IN COCOA LANDSCAPE (3PRCL)

JUABESO- BIA HOTSPOT INTERVENTION AREA (HIA)

INTRODUCTION

BACKGROUND:

The Ghana Cocoa Forest REDD+ Programme (GCFRP) is the premier emission reduction programme fully developed from a 25-year Ghana REDD+ Strategy (GRS) by the Government of Ghana through the Forestry Commission and Ghana Cocoa Board (Cocobod) with funding support from the Forest Carbon Partnership Facility (FCPF) of the World Bank. The programme seeks to significantly reduce carbon emissions resulting from cocoa expansion into forests through the promotion of appropriate climate-smart cocoa production approaches, including intensification and yield enhancement. The programme spans a mosaic landscape that produces commodities of international and national importance; - cocoa, timber, palm oil, food crops. However, the dominant crop in the landscape and also of national importance is the cocoa from which the programme derives the name “Ghana Cocoa Forest REDD+ Programme”.

Cocoa is Ghana’s most important agricultural commodity, accounting for roughly 57 percent of all agricultural exports and supporting the livelihoods of about 2.5 million rural farmers and their dependents. Cocoa production is predominant in the High Forest Zone of Ghana. The Western Region holds the largest area of remaining primary forest in Ghana and produces over 50 percent of the country’s cocoa beans. However, Ghana’s forests have come under severe threat from agricultural expansion, which is the major cause of forest loss, mainly being driven by cocoa production. This makes cocoa production the single biggest driver of deforestation in the landscape. Underlying causes for this include: limited financial and technical support for sustainable cocoa production leading to expansion into forest areas; legal disincentives to maintaining trees on farms; a lack of land use planning and landscape management; and a lack of collaboration amongst cocoa stakeholders.

The Juabeso-Bia Hotspot Intervention Area (HIA) is the first HIAs launched under the GCFRP where implementation is underway with the support of a consortium made up of Forestry Commission, Cocobod, Partnership for Forest (P4F), Touton SE, Agro-Eco, SNV and Nature Conservation Research Centre (NCRC) under the project dubbed Partnership for Productivity, Protection and Resilience in Cocoa Landscapes (3PRCL).  The 3PRCL Project which aims at increasing cocoa productivity and improving farmers’ living conditions while reducing deforestation and forest degradation within a sustainable landscape is in line with the GCFRP objectives.

In this light, there has been a need to develop a Safeguards Action Plan to inform and direct how the GCFRP implementation under the 3PRCL within the Juabeso-Bia HIA will address and respect Safeguards issues that may arise.

PURPOSE:

The UNFCCC recognizes that safeguards are a key part of REDD+ implementation and links the Cancun safeguards to results-based payment. This requires that countries implementing REDD+ should demonstrate how they have addressed and respected safeguards through the implementation of their REDD+ interventions. One of UNFCCC key priorities is ensuring that social and environmental safeguards are adhered to, throughout REDD+ process. REDD+ safeguards are designed to avoid negative social and environmental impacts and also enhance social and environmental benefits. Other REDD+ Safeguards being implemented in Ghana are; World Bank Safeguards, AFDB and National Safeguards comprising of the SESA and ESMF.

The Juabeso-Bia REDD+ Safeguards Action Plan (SAP) is been developed to guide the successful implementation of REDD+ Safeguards within the Juabeso-Bia Hotspot HIA. This SAP provides guidelines on the measures to follow in ensuring that social and environmental risks are minimize and benefits enhanced during implementation of interventions/actions within the landscape. The SAP provides measurable indicators to measure Safeguards actions and assigns responsibility of Safeguard actions to relevant stakeholders.

SCOPE:

This SAP is consistent with the UNFCCC and World Bank’s Safeguards Operational Policies and Procedures and shall assist project implementers in screening project activities for their likely social and environmental impacts and propose mitigation measures to address those risks.

All consortium partners, key stakeholders and programme implementers including safeguards teams at the district and regional levels shall refer to the Environmental and Social Management Framework (ESMF), Resettlement Policy Framework (RPF) and Pest Management Plan (PMP) for guidance.

Other REDD+ Safeguards being implemented in Ghana are; World Bank Safeguards, AFDB and National Safeguards comprising of the SESA and ESMF.

GENERAL DESCRIPTION OF HIA

Basic Administration

The district shares borders with Bia West and Asunafo North Municipal Districts to the north, Asunafo South and Sefwi Wiawso Districts to the east, Bodi District to the south, and Cote d’lvoire to the west. The district capital, Juabeso, is located 360 km to the north-west of the Sekondi-Takoradi Metropolis, the Regional Capital. The four area councils are, Kofikrom-Proso Area Council, Asempaneye Area Council, Benchema-Nkatiaso Area Council and Boinzan Area Council (GSS(a), 2014).

Traditional administration in the district is under the Sefwi Wiawso Traditional Council. Chiefs, Queen Mothers and Elders who are part of the traditional council are visible in traditional communities. The district has one of the seven divisional chiefs under the Sefwi Wiawso Paramountcy, namely, the Chief of Boinzan (Krontihene).

Figure 1:  District Map of Juabeso

The Bia West District was carved out of the Bia District in 2012 and has Essam-Debiso as its administrative capital. The district shares boundaries with the Bia East District to the north and east, Côte d’Ivoire to the west, and Juabeso District to the south. The district capital, Essam-Debiso is located 420km to the northwest of Sekondi-Takoradi and 250km from Kumasi.

The entire Bia West District falls under the jurisdiction of the Sefwi Wiawso Traditional Area with its overlord (Omanhene) residing at Sefwi Wiawso. The district has divisional and sub chiefs in the major and minor communities respectively (GSS(b), 2014). Figure 4 depicts the area map of Bia West district adapted from the District Analysis Report of the 2010 Population and Housing Census.

Figure 2: District map of Bia West

SOCIO-ECONOMIC, GEOGRAPHIC AND ENVIRONMENTAL PROFILE

The landscape encompasses the Juabeso and Bia West Districts, which together cover 265,717 ha (136,990 ha for Juabeso and 128,727 ha for Bia West), and had a total combined population of 147,374 people (just under 33,695 households) according to the 2010 census.  This represented approximately 7.6 percent of the population of the Western Region. Men slightly outnumber women in the two districts, and the population is youthful.  Rural habitation predominates, with only about one quarter of people living in urban areas in Bia West and ten percent in Juabeso. Literacy is relatively high at approximately 68 percent in both districts, though more males are reported as being literate than females.  Over three quarters of the population (77%) is economically active, with the vast majority engaged in agriculture. The entire landscape falls under the Sefwi Wiawso Paramountcy and Traditional Council.  The major ethnic groups are the Sefwi, followed by Bonos, Ashantis, people of Northern origins, and Fantes.

The main river in Juabeso is the River Sayere. It is a hilly landscape, with elevations that can reach 300-390 meters above sea level (masl). The vegetation falls within the moist semi-deciduous forest zone, and the district typically experiences two rainfall peaks (maxima) in May-June and September-October, with a dry season from November-March.

The majority of the Bia District is located within the moist evergreen forest zone, and typically experiences two main wet and dry seasons. The wet season is between April and October and the dry season is between November and March. The district is endowed with a number of rivers and streams, including the Bia River. In addition to cocoa farming and other crops, the relief and drainage of the river systems favors the development of fish farming and the cultivation of wetland rice, sugarcane and dry season vegetables.

ACTION PLAN MATRIX

| 3PRCL Project Output | Location | Safeguards Triggered | Mitigation Actions/Criteria | Indicator (Qualitative and Quantitative) | Partner Institutions | Budget (GBP) |
| --- | --- | --- | --- | --- | --- | --- |
|  | OUTPUT 1: LANDSCAPE GOVERNANCE AND FOREST PROTECTION |  |  |  |  |  |
|  | - Operationalise landscape governance and safeguard systems |  |  |  |  |  |
| Activity A.1 Setting up Sub HIAs Structures | Asempanaye, Juabeso, Akatiso Bonsu Nkwanta, New Papase, Elluokrom, Kwambikrom, Essam, Yawmatwa and Manzan, Krokosue, Juabeso, Debe | Transparent and effective national forest governance structures, Full and effective participation of relevant stakeholders | Where there are grievances on participation and gender inclusiveness, use the FGRM to resolve such grievances. | Provide reports on how sub-HIAs were set up Provide description and evidence of how (Safeguards Governance structure, HIA Governance Board, Consortium, CREMA, etc.) are formed. Records of number of grievances received and percentage addressed Number and attendance rates of stakeholder representatives at meetings recorded | Touton SA, SNV and Nature Conservation Research Centre (NCRC), Tropenbos Ghana, Rainforest Alliance, Conservation Alliance, MLNR under the 3PRCL project |  |
| Activity A.1.1 Profiling of cohort of Sub-HIAs for pilot and expansion (2 sub HIAs) | Accra office job | Full and effective participation of relevant stakeholders | Where there are grievances on participation and gender inclusiveness use the FGRM to resolve such grievances | Provide reports on how grouping of sub-HIAs were done | Nature Conservation Research Centre (NCRC) under the 3PRCL | 0.00 |
| Activity A.1.2 Setting up of basic governance units in profiled communities | Asempanaye, Juabeso, Akatiso Bonsu Nkwanta, New Papase, Elluokrom, Kwambikrom, Essam, Yawmatwa and Manzan, Krokosue, Juabeso, Debe | Transparent and effective national forest governance structures, Full and effective participation of relevant stakeholders | Where there are grievances on participation and gender inclusiveness use the FGRM to resolve such grievances. | Provide reports on the strategy for setting up of the basic governance units in the Communities within the 3PRCL project area. Reports on number of grievances recorded Number of grievances addressed | Touton SA, SNV and Nature Conservation Research Centre (NCRC), Tropenbos Ghana, Rainforest Alliance, Conservation Alliance, MLNR | 11,200 |
| Activity A1.3 Zoning of sub-HIAs (actual polygons), negotiate boundaries (in case of overlap between two Sub-HIA), and byelaws of Sub-HIA. | Asempanaye, Juabeso, Akatiso Bonsu Nkwanta, New Papase, Elluokrom, Kwambikrom, Essam, Yawmatwa and Manzan, Krokosue, Juabeso, Debe | OP 4.12 On Involuntary Resettlement Transparency and effectiveness of national forest governance Full and effective participation of relevant stakeholders | When there are resettlement issues the Resettlement Policy Framework (RPF) should be used to resettle Project Affected People (PAPs) within sub-HIAs | Provide records on description of any resettlement processes that took place Reports on compensation if any | FC, Touton SA, SNV and NCRC | 7,000 |
| Activity A1.4 Documentation and mapping of Sub-HIAs leading to devolution. | Accra, Kumasi office job | Not triggered |  |  | FC, Touton SA, SNV and NCRC | 3,500 |
| Activity A1.5 Facilitate drafting of Policy document which will allow CREMAs to act within Forest Reserves. | Accra, Kumasi office job | Full and effective participation of relevant stakeholders | Ensure that all relevant stakeholders at (national, regional district and local level) fully participate in the drafting of the policy document | Number of meetings held Report/ Minutes of meetings held | FC, Touton SA, SNV and NCRC | 0.00 |
| Activity A1.6 Support sub-HIA/CREMA to develop Constitution, Community Management Plans & implementation plans | Asempanaye, Juabeso, Akatiso Bonsu Nkwanta, New Papase, Elluokrom, Kwambikrom, Essam, Yawmatwa and Manzan, Krokosue, Juabeso, Debe | Respect for the Knowledge and rights of members of local communities Full and effective participation of relevant stakeholders | Ensure that all relevant stakeholders at (national, regional district and local level) fully participate in the development of the CREMA constitution, community management plan & implementation plans Ensure that the knowledge of CREMA/local community members is considered and respected in developing the constitution and other Community Management Plans | Records of CREMA constitution, community management plan & implementation plans Provide description and evidence of how vulnerable groups are involved in decision making | FC, Touton SA, Agro-Eco, SNV and Nature Conservation Research Centre (NCRC), Tropenbos Ghana | 10,000 |
| Activity A.1.7 Facilitate the formation of association of CREMAs/HIA Landscape Management Board | Asempanaye, Juabeso, Akatiso Bonsu Nkwanta, New Papase, Elluokrom, Kwambikrom, Essam, Yawmatwa and Manzan, Krokosue, Juabeso, Debe | Full and effective participation of relevant stakeholders | Engage all key stakeholders in the formation of CREMA/HIA Landscape management board | Report on the total number of CREMAs/HIA Landscape Management formed Records of number of meetings held Reports/minutes of meetings held | FC, Touton SA, Agro-Eco, SNV and Nature Conservation Research Centre (NCRC), Tropenbos Ghana | 2,720 |
| Activity A.1.8 Manual development and Training of sub-HIAs on governance structure, constitution, bylaws and enforcement | Accra, Juaboso and Bia District | The full and effective participation of relevant stakeholders, in particular local communities Respect for the knowledge and rights of indigenous peoples and members of local communities | Ensure that stakeholders in sub-HIAs participate in the manual development and are adequately trained | Report on training workshop held Total number of participants recorded Number of workshops held | FC, Touton SA, Agro-Eco, SNV and Nature Conservation Research Centre (NCRC), Tropenbos Ghana | 15,770 |
| HIAs and Landscape Compact Structures |  |  |  |  |  |  |
| Activity A.2.1 Negotiate and finalize Compact Agreement in the light of CFI developments | Accra, Kumasi | Transparency and effectiveness of national forest governance Full and effective participation of relevant stakeholders | Use the FGRM to resolve grievances when they arise | Description and evidence of how existing negotiation and finalization of Compact Agreement has been executed | Cocobod, P4F, Touton SA, Agro-Eco, SNV, NCRC, Tropenbos Ghana, Solidaridad, Eliho | 3,520 |
| Activity A.2.2 Get Compact Agreement signed by key stakeholders | Accra, Kumasi | Transparency and effectiveness of national forest governance Full and effective participation of relevant stakeholders | Ensure that compact agreement is signed by all key stakeholders. | Records of signed agreements | Cocobod, P4F, Touton SA, Agro-Eco, SNV, NCRC, Tropenbos Ghana, Solidaridad, Eliho | 7,000 |
| Activity A.2.3 Inaugurate HIA landscape management board. | Juaboso, Essam | Full and effective participation of relevant stakeholders | Ensure that all relevant stakeholders wihin the Juabeso-Bia landscape fully participate in the inauguration program | Records of the total number of participants for the that attended the inauguration | Cocobod, P4F, Touton SA, Agro-Eco, SNV, NCRC, Tropenbos Ghana, Solidaridad, Eliho, MLNR | 2,720 |
| Activity A.2.4 Secure agreement on HIA-Consortium Implementation Committee | Accra, Kumasi, Juaboso, Essam | Not triggered |  |  | Cocobod, P4F, Touton SA, Agro-Eco, SNV, NCRC, Tropenbos Ghana, Solidaridad, Eliho | 2,720 |
| Activity A.2.5 Finalise and operationalise HIA/sub HIAs Landscape management plan (scope of responsibilities, action plans) | Juaboso, Essam | Not triggered |  |  | Cocobod, Touton SA, Agro-Eco, SNV, NCRC, Tropenbos Ghana, Solidaridad, MLNR | 0.00 |
| Activity A.2.6 Have HIA enter into formal partnership Agreements (MOU) with External stakeholders “Consortium or Compact” and execute Agreement | Juaboso, Essam | Full and effective participation of relevant stakeholders | Ensure HIA’s partnerships with external stakeholders are properly documented. Use FGRM to address grievances received from decision making bodies. | Number of MOUs/ Agreement signed among stakeholders | Cocobod, Touton SA, Agro-Eco, SNV and NCRC | 2,720 |
| Activity A.2.7 Capacity building of community leaders, CREMA executives, landscape management boards on group development, illegal logging, dumping, mining, etc | Asempanaye, Juabeso, Akatiso Bonsu Nkwanta, New Papase, Elluokrom, Kwambikrom, Essam, Yawmatwa and Manzan, Krokosue, Juabeso, Debe | The full and effective participation of relevant stakeholders | Ensure that the capacities of local communities and other stakeholders are fully built Use REDD+ communication strategy to engage relevant stakeholders | Report on Capacity building workshops held Attendance list/Picures of participants engaged | FC, Cocobod, Touton SA, NCRC, Agro Eco, SNV CREMA executives, landscape management boards | 11,000 |
| Activity A.2.8 Coaching, monitoring and trainings for above activities | Asempanaye, Juabeso, Akatiso Bonsu Nkwanta, New Papase, Elluokrom, Kwambikrom, Essam, Yawmatwa and Manzan, Krokosue, Juabeso, Debe | Not triggered |  |  | Cocobod, Touton SA, Agro-Eco, SNV, NCRC, Tropenbos Ghana, Solidaridad, | 0.00 |
| Activity A.3 Population of the safeguards information system (SIS)/capacity building | Juaboso, Essam | Transparent and effective national forest governance structures, Full and effective participation of relevant stakeholders | Ensure that the right information is populated in the SIS. Training on SIS should be organized for all relevant stakeholders | Documented evidence for populated SIS. Training outline or agenda of capacity building. | FC |  |
| Activity A.3.1 Identification of indicators for the SIS |  | Completed |  |  |  |  |
| Activity A.3.2 Training of 3PRCL Staff and refresher training on safeguards and sensitization on the Principles, Criteria and Indicators (PCIs) for stakeholders within the Juabeso-Bia HIA | Juaboso | Full and effective participation of relevant stakeholders | Ensure that the capacities of Safeguards focal persons within the Juabeso-Bia HIA landscape are fully built | Reports on capacity building workshop held forSFPs Number of particpants recorded with attached particpants list, pictures, etc. | NRS, SFPs, Touton SA | 2,520 |
| Activity A.3.3 Training of stakeholders on safeguards data collection and sensitization on the SIS web platform within the Juabeso-Bia Landscape | Asempanaye, Juabeso, Akatiso Bonsu Nkwanta, New Papase, Elluokrom, Kwambikrom, Essam, Yawmantwa and Manzan | Full and effective participation of relevant stakeholders | Ensure that the capacities of SFPs on the SIS web platform are fully built | Reports of capacity building workshop held forSFPs Number of particpants recorded with attached particpants list | NRS, SFPs, Touton SA | 2,520 |
| Activity A.3.4 Refresher training on gender responsive activity planning for relevant stakeholders in the Juabeso-Bia Landscape led by the SFP | Asempanaye, Juabeso, Akatiso Bonsu Nkwanta, New Papase, Elluokrom, Kwambikrom, Essam, Yawmantwa and Manzan | The full and effective participation of relevant stakeholders | Ensure that the project involves both men and women in decision making Ensure that at least 30% of women are represented during programs/activities Where there are grievances on gender inclusiveness use the FGRM to resolve such conflict | Reports on the description and evidence of how vulnerable groups are involved in decision making. Number of vulnerable groups involved in decision making | SFPs, Arbitration Panel, NRS, Touton | 2,520 |
| Activity A.3.5 Sensitization and operationalization of the Feedback Grievance Redress Mechanism (FGRM) in the Juabeso-Bia HIA (including printing of FGRM posters) | Asempanaye, Juabeso, Akatiso Bonsu Nkwanta, New Papase, Elluokrom, Kwambikrom, Essam, Yawmatwa and Manzan, Krokosue, Juabeso, Debe | The full and effective participation of relevant stakeholders | All grievances under the 3PRCL Project should be addressed with the FGRM. All aggrieved persons should walk to the nearest Forestry Commission office and lodge their complaints | Records of the number/ Percentages of grievances received and addressed through the FGRM. Evidence of active use of appropriate procedures or mechanisms for resolving conflicts or grievances | SFPs, Arbitration Panel, Cocobod, Touton SA, Agro-Eco, SNV and NCRC | 1,000 |
| Build landscape resilience through community engagement, empowerment and community participation |  |  |  |  |  |  |
| Activity B.1 Community Service Concept Approach | Asempanaye, Juabeso, Akatiso Bonsu Nkwanta, New Papase, Elluokrom, Kwambikrom, Essam, Yawmatwa and Manzan, Krokosue, Juabeso, Debe | Full and effective participation of relevant stakeholders Respect for the knowledge and rights of indigenous peoples and members of local communities | Ensure that the Juabeso-Bia community members and other relevant stakeholders are considered in the establishment of the community service concept approach. | Evidence or reports on community service approach inculcated in 3PRCL project Action Plan. | Touton SA, P4F, SNV, AgroEco, FC, Cocobod |  |
| Activity B.1.1 Organize annual “Good Forest Stewardship Cup” Football tournament to create awareness, empower women, support community forest guards, protect forest and market climate smart cocoa and illustrate how all partners work together to implement landscape Governance. The Football will continue to be used as a branding tool to attract all stakeholders and consumers to join the ‘Forest Caretakers’ Movement. | Asempanaye | Full and effective participation of relevant stakeholders | Ensure that all relevant stakeholders in the Juabeso-Bia project landscape are involved in all awareness creation programs, women empowerment, forest protection. | Provide full list of participants in capacity building and awareness creation engagements | FC, Cocobod, Touton SA, Agro-Eco, SNV, NCRC, Tropenbos Ghana | 17,000 |
| Activity B.1.2 Engagement of Ghanaian football icon to promote, facilitate and provide tournament format | Accra | Not triggered |  |  |  | 5,000 |
| Activity B.1.3 Support and facilitate forest protection and awareness creation based on football icon's advice. | Asempanaye, Juabeso, Akatiso Bonsu Nkwanta, New Papase, Elluokrom, Kwambikrom, Essam, Yawmatwa and Manzan, Krokosue, Juabeso, Debe | Full and effective participation of relevant stakeholders | Ensure that all relevant stakeholders in the Juabeso-Bia project landscape are involved in all awareness creation programs, women empowerment, forest protection. | Provide full list of paarticipants in capacity building engagements | Community members, FC, Cocobod, Touton SA, Agro-Eco, SNV and NCRC | 8,000 |
| Activity B.1.4 Engagement of National Commission for Civic Education to prep women groups for a theatre piece in 15 communities (linked to deforestation/forest protection) | Asempanaye, Juabeso, Akatiso Bonsu Nkwanta, New Papase, Elluokrom, Kwambikrom, Essam, Yawmatwa and Manzan, Krokosue, Juabeso, Debe | The full and effective participation of relevant stakeholders | The 3PRCL project should ensure that at least 30% of women participate in meetings or programmes. | Description and evidence of how vulnerable groups are involved in decision making | Cocobod, FC, P4F, Touton SA, Agro-Eco, SNV and MMDAs. | 6,000 |
| B.2 Development of deforestation monitoring system for BIA Juaboso Landscape Full Traceability |  |  |  |  |  |  |
| Activity B.2.1 Collect land use change data across landscape to Improve the detection and identification of high deforestation risk areas and establish monitoring system (delineate cocoa, cocoa agroforest, forest) | Asempanaye, Juabeso, Akatiso Bonsu Nkwanta, New Papase, Elluokrom, Kwambikrom, Essam, Yawmatwa and Manzan, Krokosue, Juabeso, Debe | OP 4.01 Environmental Assessment OP 4.36 on Forests Actions to address the risks of reversals Actions are consistent with the conversation of natural forest and biological diversity | Ensure that the NFMS is effectively used to collect and monitor deforestation within the Juabeso-Bia Landscape | Information on how land use change data is collected across landscape Records on expected improvement in detection and identification of high deforestation risk areas Number of high deforestation risk areas recorded | Cocobod, FC, Touton SA, Agro-Eco, SNV and NCRC | 10,500 |
| Activity B.2.2 Map/profile all cocoa farms (legal & illegal) in forest reserves, national parks, wildlife sanctuaries, wildlife resources reserves | Juaboso and Bia Districts | Actions to reduce displacement of emissions OP 4.36 on Forest OP 4.04 Natural Habitat OP 4.12 on Involuntary Resettlement | Use the Rettlement Policy Framework (RPF) and compensation framework to resettle and compensate PAP | Number of all mapped cocoa farms (legal & illegal) in forest reserves, national parks, wildlife sanctuaries, wildlife resources reserves | Cocobod, FC, Touton SA, SNV | 22,500 |
| Activity B.2.3 Establish and declare a mitigation action plan for illegally sourced cocoa | Accra | OP 4.36 on Forest Actions to address the risks of reversals | Implemet mitigation actions to address risks of reversals | Reports on mitigation actions implemented | Cocobod, FC, Touton SA, Agro-Eco, SNV and NCRC | 18,000 |
| Activity B.2.4 Deforestation Monitoring System | Accra | OP 4.36 on Forest Transparent and effective national forest governance structures | Ensure that robust deforestation monitoring system is developed and used for monitoring deforestation Use CREMA systems to monitor deforestation ctivities | Records on the extent and the natureof deforestaton documented | FC, SNV, EPA, Touton SA | 7,500 |
| Activity B.2.5 Operationalise NFMS data protocols, templates etc. | Accra | Full and effective participation of relevant stakeholders Transparent and effective national forest governance structures | Ensure the full and effective operationalisation of NFMS data protocols and its compliance with national and local structures. | Report on how the NFMS data protocols was operationalized | FC, SNV, EPA, Touton SA | 5,000 |
| Activity B.2.6 Build capacity of frontline foresters on deforestation alert system | Juaboso, Accra, Sefwi Wiawso | Full and effective participation of relevant stakeholders | Ensure that all frontline staff of the FC capacities are built on the deforestation alert system Where grievance on participation arise use the FGRM to address those grievances | Training outline/agenda for capacity building workshop Report of capacity building workshop Records of the number of grievances addressed | Cocobod, FC, Touton SA, SNV | 2,020 |
| Activity B.2.7 Organize training in community based forest monitoring for 30 communities | Juaboso and Bia Districts | Full and effective participation of relevant stakeholders | Ensure inclusiveness of vulnerable groups in community training and utilize FGRM for addressing grievances. Ensure full and effective participation of local stakeholders. | Documented evidence of training outline/agenda for the 30 communities. engaged Records of the number of grievances addressed. | Cocobod, FC, Touton SA, SNV and NCRC communities | 3,950 |
| Activity B.2.8 Pilot implementation of land use plans and forest monitoring by strengthening community resources management Areas, reserve boundary monitoring CREMAs in forest protection (this will involve land use zoning) | Asempanaye, Juabeso, Akatiso Bonsu Nkwanta, New Papase, Elluokrom, Kwambikrom, Essam, Yawmantwa and Manzan | Full and effective participation of relevant stakeholders | Ensure that all community resources management Areas are fully and effectively engaged in pilot implementation of land use plans and forest monitoring. | Reports on pilot activities on landuse plans by stakeholders Records on the number of CREMA members involved in training programs on landuse zoning and forest protection | FC, Touton SA, SNV CREMAs | 3,950 |
| Activity B.2.9 Establish forest monitoring baseline and map risk zones, for Juaboso -Bia landscape (GIS based) | Juaboso and Bia Districts | That actions are consistent with the conservation of natural forest and biological diversity Natural habitats Transparent and effective national forest governance structures Full and effective participation of relevant stakeholders | Use the Forest Reference level to establish forest monitoring baseline and map risk zones for the Juabeso-Bia HIA landscape Provide instruments (Drones, cameras etc) for an effect forest monitoring and risk assessment | Reports on established forest monitoring baseline and maped risk zones | FC, Touton-SA, NCRC, SNV | 48,000 |
| Activity B.2.10 Develop and implement landscape monitoring system and real-time alerts systems for early warning (GIS based) | Juaboso and Bia Districts | Transparent and effective national forest governance structures Full and effective participation of relevant stakeholders | Involve all relevant stakeholders in the developments and monitoring of Forest Reserve and Off Reserve activities within the project area Use drones to monitor activities on Reserves | Records of the types and number of equipments used for monitoring Number of stakeholders involved in the development of landscape monitoring systems Number of times monitoring exercise was undertaken | FC, Cocobod, Touton SA, SNV, NCRC | 10,500 |
| Activity B.2.11 Develop and apply protocols for operationalising alert system at landscape | Juaboso and Bia Districts | Full and effective participation of relevant stakeholders | Involve all relevant stakeholders in the developments and application of protocols for operationalizing alert system within the project area | Records of the number of stakeholders involved in the development of the alert systems | FC, Cocobod, Touton SA, SNV, NCRC, AgroEco, CREMAs | 5,000 |
| Activity B.2.12 Improve the detection and identification of high deforestation risk areas and establish monitoring system (delineate cocoa, cocoa agroforest, forest) | Juaboso and Bia Districts | That actions are consistent with the conservation of natural forest and biological diversity OP 4.36 on Forest | Use the NFMF to develop an improved system to detect and identify risk areas for cocoa production, forest areas | Records of an improved Forest monitoring system | FC, Cocobod, Touton SA, SNV, NCRC, AgroEco, CREMAs | 21,000 |
| Activity B.2.13 Improve a web-based display platform to visually demonstrate no-deforestation in supply chains | Virtual | Transparent and effective national forest governance structures That actions are consistent with the conservation of natural forest and biological diversity | Populate the Safeguards Information system with data on no-deforestation in supply chains to ensure transparency Use the NFMF to develop an improved wen-based platform to demonstrate no deforestation free supply chain | Evidence of an improved web platform Data on areas showing no deforestation | FC, Cocobod, Touton SA, SNV, NCRC, AgroEco, CREMAs | 7,000 |
| SUSTAINABLE COCOA PRODUCTIVITY IMPROVEMENTS |  |  |  |  |  |  |
| Activity C Implement climate smart standard to bring multiple actors together and measure & report on sustainability outcomes at the landscape scale |  |  |  |  |  |  |
| Activity C.1 Finalise certification procedures for Climate Smart Cocoa Standard | Accra | Not triggered |  |  |  |  |
| Activity C.1.1 Stakeholder engagements and workshop to finalize technical inputs on draft CSC standard | Juaboso and Bia Districts | The full and effective participation of relevant stakeholders, in particular indigenous peoples and local communities. | Ensure stakeholders are engaged to finalize technical inputs on draft CSC standard. Ensure participation of farmers and community members on climate smart principles. | Proceedings from workshop and level of engagement. Number of farmers and community members involved in training sessions. | Cocobod, FC, Touton SA, Agro-Eco | 4,000 |
| Activity C.1.2 Political/governmental accent for CSC standard secured | Accra | Transparent and effective national forest governance structures, taking into account national legislation and sovereignty | Ensure government accent is transparent and compliant to CSC standard. | Documentation of due proceedings in securing accent. Document evidence of governement accent. | MMDAs, Cocobod, FC | 0.00 |
| Activity C.1.3 Sensitize stakeholders, particularly cocoa companies, on CSC and set date on which mandatory requirement begin | Accra, Kumasi, Wiawso | The full and effective participation of relevant stakeholders, in particular indigenous peoples and local communities. | Ensure sensitization workshops includes all stakeholders especially vulnerable groups (women, youth). | Action plan for sensitization workshop. Number of stakeholders and vulnerable groups involved in sensitization. | Cocobod, FC, Touton SA, WCF, CFI | 5,800 |
| Activity C.1.4 Set implementation timetable and roll out | Accra | The full and effective participation of relevant stakeholders, in particular indigenous peoples and local communities | Ensure all stakeholders are involved in timetable setting and implementation. | Documented evidence of implementation timetable . Number of stakeholders involved in setting timetable and implementation. | Cocobod, FC, WCF, CFI | 0,00 |
| Activity C.1.5 Track monthly adoption rate of climate smart cocoa principles on farms. | Juaboso and Bia Districts | Not triggered |  |  |  |  |
| Activity C.1.6 Implement landscape level Criteria (Stakeholder Partnership, Community Engagement, Landscape Management Support & Facilitation, MRV that measures Sustainability Outcomes at the landscape scale) | Juaboso and Bia Districts | The full and effective participation of relevant stakeholders, in particular indigenous people and local communities | Ensure relevant stakeholders are involved in implementing landscape and farm level Criteria. | Documented evidence of stakeholder engagements. Number of stakeholders engaged. | Cocobod, FC, Touton SA, Agro-Eco, SNV | 9,000 |
| Activity C.1.7 Implement farm level Criteria (Training and Extension, Support Systems, Market Access, Incentive and Livelihood Packages,Research, Monitoring and Evaluation, Data Management and ICT Tools) | Juaboso and Bia Districts | The full and effective participation of relevant stakeholders, in particular indigenous people and local communities | Ensure relevant stakeholders are involved in implementing landscape and farm level Criteria. | Documented evidence of stakeholder engagements. Number of stakeholders engaged. | Cocobod, FC, Touton SA, Agro-Eco, SNV | 9,000 |
| Activity C.1.8 Conduct landscape level audit to produce a climate smart cocoa (deforestation-free) certificate and report to industry | Juaboso and Bia districts | Not triggered |  |  |  | 20,000 |
| Improved service delivery efficiency for long-term climate smart cocoa production |  |  |  |  |  |  |
| Activity D.1 Improved climate change adaptation, mitigation of greenhouse gases emissions and increase carbon sequestration, and Biodiversity protection. | Juaboso and Bia Districts | Actions to address the risks of reversals | Ensure that intervention enhances biodiversity protection and doesn’t trigger the risk of reversals. | Documented and observational evidence of improvement in climate change adaptation, mitigation of greehouse gases, increased carbon sequestration and biodiversity protection. | Cocobod, FC, Touton SA, Agro-EcoSNV, NCRC |  |
| Activity D.1.1 Build capacity of trainers, including lead farmers, to disseminate recommended practices and support farmers with appropriate Training and materials. | Juaboso and Bia districts | The full and effective participation of relevant stakeholders, in particular local communities | Ensure lead farmers are adequately trained and equipped with the necessary training materials. Ensure lead farmers disseminate information/knowledge gained to other farmers | Document training sessions of lead farmers. Number of lead farmers trained. Evidence of leade farmers training other farmers on recommended practices | FC, Cocobod, Touton SA, NCRC, SNV. Agro Eco | 1,920 |
| Activity D.1.2 Conduct in-field monitoring and coaching on the implementation of interventions. | Juaboso and Bia districts | The full and effective participation of relevant stakeholders, in particular local communities | Ensure that all relevant stakeholders are involved in field monitoring and implementation of project interventions Where there are grievances use the FGRM to resolve such grievances | Report on field monitoring Number of grievances recorded | FC, Cocobod, Touton SA, NCRC, SNV. Agro Eco, CREMAs | 13,500 |
| Farm level training, professionalization and coaching |  |  |  |  |  |  |
| Activity D.2.1 Organize farmer business school, Segmentation of farmers, succession planning. | Juaboso and Bia districts | The full and effective participation of relevant stakeholders, in particular indigenous peoples and local communities | Ensure a well organised establishment of farmer business schools and effective participation of farmers. | Documented evidence of training outline and strategy used in business schools. Assesment of perfomance and participation of farmers. Number of schools estblished and farmers enrolled. | Cocobod, FC, Touton SA, Agro-Eco | 27,000 |
| Activity D.2.2 Train farmers and community on climate smart principles. | Juaboso and Bia districts | The full and effective participation of relevant stakeholders, in particular indigenous peoples and local communities | Ensure effective training process and full participation of farmers. | Documented evidence of training outline and strategy used. Assesment of perfomance and participation of farmers. Number of training sessions held and farmers involved | Cocobod, FC, Touton SA, Agro-Eco, SNV | 16,000 |
| Activity D.2.3 Support farmers to create and implement Farm Business Plan | Juaboso and Bia districts | The full and effective participation of relevant stakeholders, in particular indigenous peoples and local communities | Ensure effective support system and full participation of farmers in creating and implementing Farm Business Plan | Prove of support to farmers and how it influenced their activities Assesment of perfomance and participation of farmers. | Cocobod, FC, Touton SA, Agro-Eco | 9,000 |
| Cocoa Rehabilitation |  |  |  |  |  |  |
| Activity D.3.1 Identify old/diseased cocoa farms and rehabilitate | Juaboso and Bia districts | Full and effective participation of relevant stakeholders Environmental Assessment Physical Cultural Resources Pest Management Natural habitat | Compensate farmers for affected cocoa trees felled Provide access to planting materials (cocoa and tree seedlings and technical support) to project affected famers. Rehabilitate old cocoa farms Apply biological methods to control pests | Type of compensation (monetary or non-monetary) paid to PAPs Records on the number of old/diseased cocoa farms cut down and rehabilitated Method or strategy used in identifying old/diseased cocoa farms. | Cocobod, FC, Touton SE, Agro-Eco, SNV | 10,000 |
| Activity D.3.2 Site verification by Cocobod | Juaboso and Bia Districts |  |  |  |  | 7,500 |
| Activity D.3.3 Capacity building _coops Institutional oversight and service delivery | Juaboso and Bia Districts | Full and effective participation of relevant stakeholders | Ensure effective training process and full participation of coops. | Documented evidence of training outline and strategy used. Assesment of perfomance and participation of coops Number of training sessions held and coops involved | Cocobod, FC, Touton SE, Agro-Eco, SNV | 12,000 |
| Activity D.3.4 Organize Cocoa coops radio programme | Juaboso and Debiso | Full and effective participation of relevant stakeholders | Outline and establish a consistent and engaging radio programme outline with focus on cocoa coops. | Number of radio stations engaged and programme sessions. Number of call ins during program | Cocobod, FC, Touton SE, Agro-Eco, SNV | 10,000 |
| Activity D.3.5 Joint meetings with COCOBOD | Accra | Full and effective participation of relevant stakeholders | Ensure effective collaboration and equal opportunity of participation for all stakeholders during meetings. | Documented evidence of minutes and meeting outline. Number of times meetings were held | Cocobod, FC, SNV, Partnership for Forest (P4F), Touton SA, Agro-Eco | 2,400 |
| Activity D.3.6 Workshop on Rehab & Renovation for Traditional Leader/Land owners |  | Full and effective participation of relevant stakeholders Respect for the knowledge and right of local people | Ensure that workshop is designed and executed to meet the understanding of particiants (traditional leaders/land owners) ensure that measures are put in place to attract full participation of traditional leaders/land owners. | Documented evidence of training outline and strategy used. Assesment of perfomance and participation of traditional leaders/land owners. Number of workshop training sessions held and participants involved | Cocobod, FC, Touton SA, Agro-Eco | 5,050 |
| Activity D.3.7 Develop communication strategy for integrated awareness programmes on Rehab and Renovation |  | Full and effective participation of relevant stakeholders | In consultation with relevant stakeholders, outline and establish a consistent and engaging communication strategy for integrated awareness programmes on rehab and innovation | Strategy document with details on stakeholders involved, process of developing the strategy, and the outcomes. | Cocobod, FC, Touton SA, SNV, Agro-Eco | 10,000 |
| Activity D.3.8 Support to coops group meetings (inceptions) |  | Full and effective participation of relevant stakeholders | Develop a meeting outline to guide the proceedings of the coops group meeting. Provide both technical and material support to ensure effective meetings outcome Ensure full and effective participation of all members in the coops group meeting. | Documented evidence of the kind of support (technical or material) offered. Number of meetings held and coops involved | Cocobod, FC, Touton SA, SNV, Agro-Eco | 4,500 |
| Timber in Cocoa Agroforestry |  |  |  |  |  |  |
| Activity D.4.1 Sensitization of farmers on the Timber in Cocoa Agroforestry scheme | Juaboso and Bia districts | Full and effective participation of relevant stakeholders | Develop an effective sensitization approach that will engage the farmers on Timber in Cocoa Agroforestry Scheme. | Description of sensitization methodology/strategy And its effectiveness Assesment of performance and participation of farmers in sensitization Number of farmers engaged in the sensitization. | Cocobod, FC, Touton SA, SNV, Agro-Eco | 9,000 |
| Activity D.4.2 Formulate sustainable forestry management scheme, FSC certification | Juaboso and Bia districts | That actions complemement or are consistent with objectives of National Forest Progammes and relevant international conventions | Ensure interventions shall enhance and promote effective strategies that maintain, conserve and restore biodiversity and ecosystem services. | Evidence of a sustainable forestry management scheme, FSC certification Formulation procedure and the stakeholders involved | Cocobod, FC, Touton SA, Agro-Eco | 10,000 |
| Activity D.4.3 Local stakeholder consultative workshops/meetings | Juaboso and Bia districts | Full and effective participation of relevant stakeholders | interventions shall identify gaps among local stakeholders and organise necessary capacity building workshops to ensure effective participation of all stakeholders. | Documented evidence of workshops/meeting outline and outcome Number of workshop training sessions held and participants involved | Cocobod, FC, Touton SA, SNV, Agro-Eco | 18,080 |
| Activity D.4.4 Capacity building of existing youth teams on cocoa agroforestry best practices (This will include capacity building of CRMC to set up database to register planted trees and for monitoring) | Juaboso and Bia Districts | Full and effective participation of relevant stakeholders | Interventions shall identify gaps among existing youth teams and organise necessary capacity building workshops to ensure effective participation. | Documented evidence of workshops/meeting outline and outcome Number of workshop training sessions held and participants involved | Cocobod, FC, Touton SA, SNV, Agro-Eco | 10,080 |
| Activity D.4.5 Acquisition of 100,000 high value timber species | Juaboso and Bia districts | Not tiggered |  |  |  | 30,000 |
| Activity D.4.6 Support youth teams to plant and maintain 1,000 hectares of cocoa farms including marginal lands | Juaboso and Bia districts | Full and effective participation of relevant stakeholders | Provide youth teams with activity schedule and action plan to guide their planting exercise and ensure effective participation. Ensure an Environmental Impact Assesment is done. | Description of type of support offered Map evidence of planted and maintained 1,000 hectares of cocoa farms and marginal lands. | Cocobod, FC, Touton SA, Agro-Eco | 50,000 |
| Activity D.4.7 Set up cocoa agroforestry Demo farms, spic and span cocoa, series of shade trees, other trees/options | Juaboso and Bia districts | That actions complemement or are consistent with objectives of National Forest Progammes and relevant international conventions | Ensure interventions shall enhance and promote effective strategies that maintain, conserve and restore biodiversity and ecosystem services. Undetake screening to decide if an EIA will be required. | Evidence of cocoa agroforestry Demo farms, spic and span cocoa, series of shade trees, other trees/options and its influence on biodiversity and ecosystem conversation in the implementation area Number of farms established and labour that were involved. | Cocobod, FC, Touton SA, SNV, Agro-Eco | 5,000 |
| Activity D.4.8 Development of training materials and tools (including manuals) for agroforestry model implementation | Accra | Full and effective participation of relevant stakeholders | Ensure that all stakeholders are effectively involved in the development of the training material and tools for the agroforestry model implementation | Number of particpants engaged Report on engagement | AgroEco | 8,500 |
| Access to inputs and integrated services |  |  |  |  |  |  |
| Activity D.5.1 Provision of Start-up kits for 30 service providers (Youth Entrepreneurs) | Juaboso and Bia districts | Full and effective participation of relevant stakeholders | Ensure fair and effective distribution of start-up kits for service providers (Youth Entrepreneurs) | Description and evidence of the strategy used to provide Start-up kits for the service providers Description of how provisions of the start-up kits influenced implementation of 3PRCL | Touton SA, | 24,000 |
| Activity D.5.2 Set up, train and equip youth teams in the communities to provide farm management services such as pruning, grafting, spraying, replanting for farmers on agreement/contract (Agro Eco) | Juaboso and Bia districts | Full and effective participation of relevant stakeholders | Develop a training manual that will ensure the full participation of youth teams in the communities. | Documented evidence of workshops/meeting outline and outcome Number of training sessions held and participants involved | Cocobod, FC, Touton SA, SNV, Agro-Eco | 16,000 |
| Activity D.5.3 Provide agro-services and inputs support for 2 RSCs | Kofikrom/Proso and Bonsu nkwanta | Pest management plan | Ensure effective use of biological and evironmental control methods for pest management. Use the pest management plan to ensure that health and environmental hazards associated with pest are minimized. | Evidence of reduced pesticide use and pest issues within 3PRCL project area Number of safety equipment purchased and used. | Touton SA | 20,000 |
| Activity D.5.4 Improved seedling Distribution | Juaboso and Bia districts | Full and effective participation of relevant stakeholders | Identify gaps in the existing distribution approach and put meausres in place to improve it. Incase of grievances from victims of unfair distribution, use FGRM to address them. | Strategy document of how seedling were acquired and distributed. Evidence of improved distribution system Number of seedling distributed and receivers. | Cocobod, FC, Touton SA, SNV, Agro-Eco | 20,000 |
| Activity D.5.5 Establishment of new farm demo sites (digging holes, labor etc.) and Maintenance of demo sites | Juaboso and Bia districts | OP 4.01 Environmental Assesment OP 4.04 Natural habitat | Conduct screening of farm demo sties under the 3PRCL project to determine the level of environmental assessment Conduct PER for farm demo sites of 40ha and EIA for areas above 40ha Where there are grievances, use the FGRM to address it | Provide screening reports Where PER or EIA is done provide reports on them Number description of howgrievance were addressed Number of all farm inputs used | Cocobod, FC, Touton SA, SNV, Agro-Eco | 5,000 |
| Activity D.5.6 Cocoa seedlings and planting materials development | Juaboso and Bia districts | Not triggered |  |  |  | 500,000 |
| Activity D.5.7 Maintenance of Demo plots on integrated soil fertility and crop pest management system | Juaboso and Bia districts | OP 4.01 Environmental assesment OP 4.04 Natural habitat Pest management | Conduct screening of farm demo sties under the 3PRCL project to determine the level of environmental assessment Conduct PER for farm demo sites of 40ha and EIA for areas above 40ha Where there are grievances, use the FGRM to address it Use the pest management framework to promote the use of biological and environmental control methods for pest management | Provide screening reports Where PER or EIA is done provide reports on them Number description of howgrievance were addressed Number of biological and environmental methods used for pest management Number of safety equipments purchase and distributed to farmers | FC, Cocobod, NCRC, Agro Eco, SNV, Touton SA, Community farmers | 38,500 |
| Incentive creation and Income diversification |  |  |  |  |  |  |
| Income diversification and community resilience programme |  |  |  |  |  |  |
| Activity E.1 Vegetable production, Start up kits and Demo plots | Juaboso Distict | Full and effective participation of relevant stakeholders Pest management | Involve farmers in training on vegetable production Use the Pest management framework to Promote the use of biological and environmental control methods for pest manage | Number of safety equipments purchase and distributed to farmers | Touton SA, SNV, Agro-Eco |  |
| Activity E.1.1 Provision of kits for vegetable production | Juaboso District | Not triggered |  |  | Touton SA | 5,000 |
| Activity E.1.2 Refresher training of agronomists on vegetable production | Juaboso District | The full and effective participation of relevant stakeholders | Where there are grievance on inclusiveness, participation, benefit sharing use the FGRM to resolve such grievaces | Evidence of training and number of workshops held Reports, list of participants, pictures Records of the number of grievances addressed | Cocobod, Agro Eco, SNV, Touton SA, Community farmers | 2,950 |
| Activity E.1.3 2 Commercial Demo plots established | Bonsu Nkwanta and Kofikrom | Not trggered |  |  | Touton SA | 2,400 |
| Activity E.1.4 Training of women on vegetable production | Juaboso and Bia districts | The full and effective participation of relevant stakeholders | Ensure that at least 30% of women participate in vegetable production as alternative livelihood activity under the 3PRCL | Records of the percentage/number of grievances addressed | Agro Eco, SNV, Touton SA, Community farmers | 11,250 |
| Activity E.1.5 Monitoring of vegetable demo sites (1 visit every 2months) | Juaboso and Bia districts | Transparent and effective forest governance The full and effective participation of relevant stakeholders | Use checklist for monitoring and where there are grievances use the FGRM to resolve such grievances | Evaluation or assessment report from monitoring of demo sites Description of how these interventions has impacted (positively and negatively) on biodiversity and its influence on 3PRCL Description of the number of grievances recorded | MoFA, Touton SA | 4,800 |
| Activity E.1.6 Train and promote economically viable and environmentally sound on-farm income diversification options, (e.g. promotion of natural regeneration, vegetables, spices, food crops, bee-keeping, small ruminants, etc) with a focus on women and youth groups | Juaboso and Bia districts | The full and effective participation of relevant stakeholders Respect for the knowledge and rights of local communities | Provide access to yield insurances promote marketing of additional livelihood products Ensure Sustainable Finance for HIAs activities to ensure that each HIA target area has a sound financial foundation Where there are grievances use the FGRM to resolve such grievances | Evidence of farmer access to insurance products that help them to better manage risks Availability of insurance product Number of farmers that access insurance product Availability of documented strategies to enhance revenue streams from vegetables, spices, food crops, bee-keeping, small ruminants, etc. | Cocobod, FC, Touton SA, Agro-Eco, SNV | 4,020 |
| Activity E.1.8 Explore the possibility of RSCs partnering with Telcom to improve communication in communities of operation as well as developing apps which support farm development | Juaboso and Bia districts | Not triggered |  |  |  | 0.00 |
| Activity E.1.9 Develop a sustainable financial incentive for cocoa forest landscape governance through Payments for Ecosystem Services scheme (Linked to trust fund) and trade of Emission Reductions and Carbon Credits, and recommend needed reforms: Dialogue, amend/tailor and agree on new financing approach for inputs, rehab and renovation with financial institution and farmer representatives |  | Risk management and Finance | Provide access to yield insurances Promote marketing of additional ERs above FCPF Marketing of a Ghana’s CSC brand that could create new opportunities for trading a “premium product ER Cocoa/marketing Ensure Sustainable Finance for HIAs activities to ensure that each HIA target area has a sound financial foundation | Evidence of farmer access to insurance products that help them to better manage risks Availability of insurance product Number of farmers that access insurance product Availability of documented strategies to enhance revenue streams from cocoa, NTFP harvesting, other perennial tree crops, and climate finance in each HIA. | FC, TOUTON SA, SNV | 37,800 |
| Activity E.1.10 "Sourcing of “off grade” beans through the RSCs and network of farmers" | Juaboso and Bia districts | Not triggered |  |  |  | 0,00 |
| Activity E.1.11 Train RSCs to produce compost through community compost points | Bonsu Nkwanta and Kofikrom RSCs | Full and effective participation of stakeholders | Develop a training outline and ensure the full participation of RSCs. | Documented evidence of training sessions and level of participation of RSCs Assesment of performance and participation of RSCs after the training Number of training sessions held and number of participants. | Touton SA | 1,500 |
| Activity E.1.12 Facilitate transportation, boosting the production of other (cash) crops, creating more stable food chains | Juaboso and Bia districts | Not triggered |  |  | Touton SA | 0,00 |
| Finance (access to finance for rehab and renovation) |  |  |  |  |  |  |
| Activity E.2.1 Review and aligning of cocoa coops model with Touton Supply chain | Juaboso and Bia districts | Environmental Assessment Natural Habitat Pest management Transparency and inclusiveness Respect for the knowledge and rights of local communities | Conduct screening of cocoa areas under the 3PRCL project to determine the level of environmental assessment Conduct PER for Cocoa areas of 40ha and EIA for areas above 40ha Promote the use of biological and environmental control methods for pest management Where there are grievances use the FGRM to resolve such grievances | Provide screening reports Where PER or EIA is done provide reports on them Reporton mitigation actions undertaken Number of grievance recorded and addressed Number of biological and environmental methods used for pest management Number of safety equipments purchase and use Number (percentage) of farmers that adopt climate smart cocoa practices | FC, Cocobod, NCRC, Agro Eco, SNV, Touton SA, Community farmers | 5,250 |
| Activity E.2.2 Establishment of groups, constitution, regulation, registration, incentives for member retention | Juaboso and Bia districts | Full and effective participation of relevant stakeholders | Ensure collaboration between revelant stakeholders in the establishment of groups, constitution, regulation, registration, incentives for member retention. | Documented evidence of groups, constitution, regulation, registration, and incentives created, and its effectiveness in the implementation area Strategy document for establishing the various interventions. Number of groups formed. | Cocobod, FC, Touton SA, Agro-Eco | 11,250 |
| Activity E.3 Pilot credit scoring and establish partnership | Juaboso and Bia districts | Not triggered |  |  | SNV | 0,00 |
| Activity E.3.1 Collection of financial, farm and household data of farmers in preselected target areas and establish their credit worthiness (E.g. for post replanting management - 500 farmers) | Juaboso and Bia districts | Not triggered |  |  | SNV | 20,000 |
| Activity E.3.2 Educate RSC staff/lead farmers on new financing approach | Juaboso and Bia districts | Full and effective participation of stakeholders | Ensure that all relevant stakeholders (RSC staff/lead farmers) are fully engaged on new financing approach. | Documented evidence of training sessions and level of participation of RSCs Assesment of performance and participation of RSCs after the training Number of training sessions held and number of participants. | Touton SA, SNV | 3,320 |
| Activity E.3.3 Establish partnership with MFIs/Local Banks / Donors for support | Virtual | The full and effective participation of relevant stakeholders | Enhance access to financial credit for CSC by establishing partnerships with MFIs, Local Banks and Donors | List of potential funding and credit facilities to foster good-practices for implementing climate smart cocoa production. Number of partnerships established Number of farmers who have access to credit and financial support | SNV, Touton SA | 13,500 |
| Activity E.3.4 Coops training in digital financial services, access to inputs and finance | Juaboso and Bia districts | Full and effective participation of relevant stakeholders | Ensure effective training process and full participation of Coops. | Documented evidence of training outline and strategy used. Report on training held Number of training sessions held and coops involved | Touton SA, SNV | 10,080 |
| Activity E.3.5 Documented Project experience with key learnings and recommendations to be shared with wider industry |  | Not triggered |  |  |  | 0,00 |